# Scope Extraction and Cross-Document Consistency Report

Pinnacle Industrial Holdings, Inc. / Pinnacle Hydraulics Solutions, LLC — HX-9000 Products Liability Defense

Whitford & Callaway LLP Matter No. WC-2025-04381  |  MDL No. 3:24-md-02987 (N.D. Ohio)  |  Cuyahoga County Case No. CV-24-938471

PRIVILEGED AND CONFIDENTIAL — ATTORNEY WORK PRODUCT

# 1. Purpose, Sources and Method

This report pulls out every scope-defining term in the engagement materials: parties and matters, work streams, exclusions, budgets and caps, rates, staffing, approval thresholds, reporting, success fee and termination terms, and governing-document hierarchy. It then compares each term across all six source documents and flags every place where they disagree. Each flag gets a severity rating, a view on which document controls, and a recommended fix.

| Ref | Document | Date | Status noted on face |
| --- | --- | --- | --- |
| EL | Engagement Letter (incl. Exhibits A and B) | Feb. 3, 2025 | Signature blocks blank in copy reviewed |
| MP | Matter Plan | Dated Feb. 10, 2025 (contains Mar. 28, 2025 Revision 1 content) | Signature blocks blank |
| R1 | Matter Plan Revision 1 — CPSC Regulatory Response Addendum | Mar. 28, 2025 | Dates filled in; signature lines blank (Layton / Giles only) |
| OCG | Outside Counsel Guidelines v6.2 | Eff. Jan. 1, 2024 | Signed by GC Stanhope |
| XLS | Budget Summary workbook (Fee Budget, Disbursement Allocation, Monthly Forecast tabs) | Undated (post-Mar. 28, 2025) | Working document |
| EML | Scope negotiation email chain (Layton / Voss / Giles) | Jan. 15–31, 2025 | Pre-execution negotiation record |

Severity scale: HIGH = could lead to unauthorized work, unpaid fees, a fee dispute, or a breach of a client approval requirement. MEDIUM = two documents give different figures or procedures, and the difference needs to be fixed in writing. LOW = drafting, citation, or clerical error.

Which document controls: EL §§11–12 say the EL controls over both the OCGs and the MP. MP §10 ranks them EL > OCG > MP. The OCG preamble, however, says an engagement letter overrides the OCGs only where it "expressly and specifically identifies the Guideline provision being modified." The EL never cites a specific OCG section. As a result, the "Controlling" column below states whether the answer depends on that unresolved conflict (see Finding H-1).

# 2. Executive Summary

We identified 42 inconsistencies or open items: 12 HIGH, 17 MEDIUM and 13 LOW. The most significant are:

WS-4 (CPSC) was added without the approval the EL requires. Its $320,000 sub-budget is above the 5% new-work-stream limit ($212,500) in EL §§1, 7 and 12. That limit requires the General Counsel's prior written re-approval. Revision 1 was agreed and signed only by the Billing Partner and the Deputy GC. We found no GC approval in the record.

The work-stream budgets do not agree across the documents. The MP and the XLS both total $4,250,000, but they split it differently: WS-1 is $1.85M vs $1.65M, WS-6 is $420K vs $870K, WS-7 is $345K vs $450K, and the MP includes a $360K contingency that the XLS drops. In addition, the XLS Monthly Forecast columns do not add up to the XLS's own stated totals.

The expert and disbursement budget has a $20,000 gap. The EL and MP §3.3 set expert fees at $780,000 (rebuttal reserve $230,000). MP §7.2 and the XLS use $760,000 (reserve $210,000), which brings the disbursement total to $1,330,000 against the $1,350,000 the EL approved.

The documents disagree on whether a fee-cap overage can be approved after the fact. The EL allows retroactive Deputy GC approval of overages up to 10%, within 15 business days of the invoice. The MP shortens that window to 5 business days after month-end. OCG §4.3 bans retroactive approval outright, with no de minimis exception. Because of the hierarchy conflict, it is unclear which rule applies.

"Aggregate payments", the term that drives the success fee, is still undefined. The emails show the parties disagreed (the firm wanted indemnity-only; the client wanted total cost including carrier payments) and never resolved it. Neither the EL nor the MP defines the term.

There is still a gap between the non-HX-9000 exclusion (EX-6) and WS-1. EX-6 carves consolidated MDL claims back in, but WS-1 covers only the MDL "as currently constituted". The MP says the carve-back does not authorize any work. The EL's version of EX-6 is broader than the MP's.

WS-5 conflicts with the EL on carrier contact. The MP authorizes "direct communication" with Fortitude and Ridgeline about coverage positions. EL §8 prohibits that without the Deputy GC's prior coordination and approval.

WS-4 is described inconsistently. Revision 1 calls the firm "coordinating counsel only", with no direct CPSC contact, yet lists VCAP submission to the CPSC and attendance at CPSC meetings as in scope. VCAP work also sits close to EX-4 (recall advice).

The contract reviewer cost has no budget line. The EL says it is billed separately and sits outside the blended rates. The MP calls it a disbursement but gives it no line. The XLS puts it inside the WS-6 fee budget. The OCGs require every reviewer to be approved by name.

The "February 10, 2025" Matter Plan already contains Revision 1 content (the March 28 revision history, WS-4, and the March 14 CPSC investigation). The executed original version cannot be identified from this copy.

# 3. Extracted Scope Terms — Cross-Document Matrix

"—" means the document does not address the term. Status: ✔ consistent; ✖ inconsistent (see finding ID in Section 4); ◐ gap or undefined.

| Term | EL | MP | R1 | OCG | XLS | EML | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Clients | Pinnacle Industrial Holdings, Inc. and PHS (§1) | Same (§1) | Same | Pinnacle and all subsidiaries (§1.1) | — | Same | ✔ |
| Covered matters | MDL 3:24-md-02987 and CV-24-938471 (§1) | Same; WS-1 limited to MDL "as currently constituted" (§3.1) | Same | — | Same | Same | ◐ M-12 |
| Plaintiff count | 43 individual + 7 corporate "in the litigation" (§1) | 43 + 7 in MDL, plus 5 separate state-court plaintiffs (§2.2) | — | — | — | — | ✖ L-6 |
| Engagement / supersession | Supersedes Phase 0 letter (Oct. 1, 2024; $175K cap; closed Dec. 20, 2024); Phase 0 excluded from budget | Same (§1, §7) | — | — | — | Same (Jan. 31) | ✔ |
| Work streams | General categories listed; regulatory response not listed (§1); EL §5.1 nevertheless refers to a "regulatory response" work stream | WS-1 to WS-3, WS-5 to WS-7 original; WS-4 added by R1; says "seven (7)" and lists six | Adds WS-4; calls WS-7 "Settlement Evaluation and Mediation Preparation" | — | WS-1 to WS-7 | WS-1 to 3, 5 to 7; Giles "confirm[s] WS-1 through WS-7" | ✖ M-14, L-3 |
| New work-stream threshold | >5% of AFB ($212,500) requires GC prior written re-approval (§§1, 7, 12) | — | WS-4 $320K; signed only by Layton / Giles | Addendum signed by DGC or GC (§4.4) | Notes §7 threshold | — | ✖ H-2 |
| Exclusions EX-1 to EX-6 | EX-1 class action; EX-2 appellate; EX-3 affirmative claims; EX-4 recall; EX-5 lobbying; EX-6 non-HX-9000 unless consolidated "or otherwise become part of the proceedings" | Same numbering; EX-6 carve-back is not an affirmative authorization; EX-3 expanded; EX-5 adds CPSC rulemaking | EX-4 and EX-5 applied to WS-4 | — | — | EX-1 appellate / EX-2 class action (numbers reversed) | ✖ M-10, H-6, L-2 |
| Aggregate Fee Budget (AFB) | $4,250,000 through end of trial; excludes success fee, expert fees, disbursements (§3.4) | $4,250,000 (§7) | $4,250,000, cited as "EL §7.1" | Budget by phase and timekeeper class required (§4.1) | $4,250,000, cited as "EL §4" | $4.25M | ✔ amount; ✖ H-3, L-1 |
| WS fee allocations | Deferred to MP | WS-1 $1.85M; WS-2 $475K; WS-3 $385K; WS-4 $320K; WS-5 $95K; WS-6 $420K; WS-7 $345K; contingency $360K | WS-4 $320K | — | WS-1 $1.65M; WS-2 $480K; WS-3 $385K; WS-4 $320K; WS-5 $95K; WS-6 $870K; WS-7 $450K; no contingency | — | ✖ H-3, H-4 |
| Budget checkpoints | 50% $2,125,000; 75% $3,187,500; report to DGC within 10 business days | Same | Same | Same for AFB >$1M (§4.2); >10% variance explanation required | Same; forecast reaches 50% in Oct. 2025 and 75% in Feb. 2026 | — | ✔ (OCG content extra — L-9) |
| Monthly fee cap | $285,000; overage up to 10% ($313,500) approvable retroactively by DGC within 15 business days of invoice; >10% needs GC prior approval; unapproved excess credited | Same cap; retroactive report within 5 business days of month-end | Applies to WS-4 | No retroactive approvals; no de minimis; excess not payable (§4.3); 80% notice by the 20th (§4.1) | Mirrors EL | ~$285K | ✖ H-5, M-8 |
| Disbursement budget | $1,350,000: experts $780K; Precept $340K; travel $155K; court reporting $75K | Table: experts $760K; total $1,330,000 (§7.2); text §3.3: $780K | $1,350,000, cited as "EL §8.1" | — | Experts $760K (reserve $210K); total $1,330,000, with a note that the stated total is $1.35M | $1.35M / ~$780K experts | ✖ H-7 |
| Expert caps | Non-MP experts require GC approval (§4.2) | Yeoh $120K; Nagarajan $185K; Renner $95K; damages TBD $150K (by June 30, 2025); rebuttal reserve $230K | — | Individual caps required; new expert needs GC approval, 15 business days' advance notice and CV (§5.3) | Same named experts; reserve $210K | Same named experts; reserve unspecified | ✖ H-7, L-10 |
| Disbursement approval | >$25K needs DGC pre-approval; reallocations >$25K need DGC approval | >$25K pre-approval; below $25K none; any reallocation needs DGC approval | >$25K, cited as "EL §8.3" | >$25K pre-approval; $10K–$25K advance notice (§5.2) | >$25K | — | ✖ M-9, L-1 |
| E-discovery vendor | Precept Analytics only, absent DGC approval | Same; SOW due within 30 days | Same (address added) | Vendor must be pre-approved (§5.4) | Same | Same | ✔ |
| Blended rates | Partner $685 / Senior Associate $475 / Junior Associate $340 / Paralegal $195 (Ex. A); increases need 90 days' notice and consent | Same | Marchetti at Partner rate | Each timekeeper must be listed by name; rates fixed for the calendar year (§§3.1–3.3) | — | Same | ✖ M-4 |
| Contract reviewers | $55/hr; separate line item; up to 15; each wave approved by DGC | $55/hr; treated as a disbursement but with no disbursement line (§7.2) | — | Each individual must be approved (§3.1) | Included in WS-6 fee budget | — | ✖ H-8, M-4 |
| Lead Trial Partner (Voss) | Max 40% of time unless GC approves; replacement needs GC consent and 15 business days' notice | 40%, adjustable by Billing Partner and Client (§5.1) | Oversight of WS-4, 10–15 hrs/month | Staffing changes need DGC or GC approval (§6.1) | — | — | ✖ M-6 |
| Second Chair (Sinclair) | Year 7 Senior Associate; up to 75% | Same; lead on WS-2, WS-3 and WS-6 | — | — | WS-2 leads listed as "Voss; Sinclair" | Same | ◐ L-8 |
| Associates / paralegals | Up to 3 junior associates, 160 hrs/month cap; up to 2 paralegals; changes notified to DGC | Junior associate rotation needs no client notice; senior associate / Of Counsel substitutions notified in monthly report | Up to 1 junior associate on WS-4; extra staffing via "MP §5.4" | Senior member substitution needs written approval; new timekeepers approved before invoice (§§3.1, 6.1) | — | Same | ✖ M-5, L-1 |
| Of Counsel (Marchetti) | "Regulatory response and insurance coverage coordination" work streams only; Partner rate | WS-4 and WS-5 only | WS-4 lead | — | WS-4 and WS-5 | Insurance plus "any regulatory work" | ✖ M-14 |
| Settlement authority | DGC ≤$3M; GC $3,000,001–$6M; Board >$6M; offers received passed to DGC within 24 hrs | Same | — | Offers notified within 24 hrs (phone) and confirmed by email within 48 hrs (§7.2) | — | Confirmed Jan. 20 | ✔ (◐ M-15 unit of measure) |
| Mediators / deadline | Joint approval by GC and Lead Trial Partner; pre-approved list in MP | Fitzsimmons, Delmonico, Tran; completion 90 days before trial: Mar. 3, 2026 (narrative) vs Feb. 28, 2026 (chart) | — | — | "Mar. 2026" | Same three; Giles may approve "on [Meg's] behalf" | ✖ M-11, L-12 |
| Reporting | Weekly Tuesday 3pm ET calls; monthly report by 5th business day; QBR by May 15, 2025 (GC and CFO; Layton and Voss attend) | Same; adds DGC to QBR; Sinclair supports | WS-4 added to each report | Monthly report must cover 30/60/90-day deadlines; diversity metrics in QBRs; max 2 attorneys at meetings | — | — | ✖ M-13, L-11 |
| Success fee | 7.5% × ($8.5M − "Actual Aggregate Payments"); "aggregate payments" undefined | Same; no definition | — | AFA must specify its calculation method (§3.2) | — | Definition disputed and unresolved | ◐ H-9 |
| Termination | 30 days' notice; files within 15 business days; accrued fees paid in 45 days; success fee forfeited or pro-rated; wind-down fee 2% if billed "in excess of" $2M | Wind-down if "$2M or more"; success fee "remains available" on termination without cause; transition ≤30 days | — | 30 days default; files within 30 business days if no timeframe set | — | — | ✖ M-16, M-17 |
| Insurance | Fortitude $5M / $10M; Ridgeline $15M follow-form; no direct carrier contact on coverage without DGC | WS-5 authorizes direct communication with carriers | Adds policy numbers | — | Same limits | Same | ✖ H-10 |
| Hierarchy | EL controls over OCG and MP (§§11, 12) | EL > OCG > MP (§10) | R1 controls over MP for WS-4 | EL controls only with an express section-specific override | — | OCGs "supplement" the EL (Giles) | ✖ H-1 |
| Meridian address | — | 1325 G Street NW, Ste 900, DC 20005 | 1100 Connecticut Ave NW, Ste 800, DC 20036 | — | — | — | ✖ L-4 |

# 4. Inconsistency and Gap Register

| ID | Severity | Issue | Sources | Analysis | Controlling | Recommended action |
| --- | --- | --- | --- | --- | --- | --- |
| H-1 | HIGH | Circular document hierarchy | EL §§11, 12; MP §10; OCG preamble | The EL says it controls over the OCGs. The OCGs say an EL overrides them only where it expressly names the specific OCG section being modified, and that general integration clauses do not count. The EL never cites a specific OCG section. On the OCGs' own terms, every EL term that departs from them (fee-cap overages, reviewer approval, staffing) is arguably ineffective. | Unresolved. The EL controls only if the OCG preamble is itself overridden, which the OCG language denies. | Sign a side letter or EL amendment that lists each OCG provision the EL modifies (§§3.1, 3.2, 4.3, 5.2, 6.1, 6.2) by section number. |
| H-2 | HIGH | WS-4 added without GC re-approval | EL §§1, 7, 12(a); R1 §§1, 2.2 and signature block; XLS WS-4 note | The EL defines 5% of the AFB as $212,500 and requires the GC's prior written re-approval for any work stream added after Feb. 3, 2025 that exceeds it. WS-4 is $320,000 (7.5%). R1 was agreed and signed only by Layton and Giles. EL §12 allows those two to amend the MP only for work streams at or below 5%. OCG §4.4 also says no work should start before the addendum is executed, yet the XLS forecasts $15,000 of WS-4 fees in March 2025, before the March 28 execution. | EL | Get the GC's written re-approval, retroactively ratifying WS-4. Confirm no WS-4 time was billed before approval. Put WS-4 invoices on hold until this is cured. |
| H-3 | HIGH | Work-stream fee allocations conflict between MP and XLS | MP §§3.1–3.7, 7.1; XLS Fee Budget tab | Both total $4,250,000 but split it differently. WS-1: $1,850,000 vs $1,650,000 (−$200K). WS-2: $475,000 vs $480,000 (+$5K). WS-6: $420,000 vs $870,000 (+$450K). WS-7: $345,000 vs $450,000 (+$105K). Contingency: $360,000 vs none (−$360K). The XLS reallocations exceed the approval authority MP §7.1 grants (DGC-approved transfers), and there is no record of any approval. | MP (incorporated into EL). The XLS has no contractual status. | Reissue the XLS to match MP §7.1, or document DGC-approved transfers and any contingency draws in writing. |
| H-4 | HIGH | XLS Monthly Forecast columns do not add up to its own totals | XLS Monthly Forecast tab | Summing the monthly figures gives: WS-1 $1,750,000 (stated $1,650,000); WS-2 $460,000 ($480,000); WS-4 $300,000 ($320,000); WS-6 $770,000 ($870,000); WS-7 $490,000 ($450,000). WS-3 and WS-5 tie. The grand total ($4.25M) and each monthly total are arithmetically correct, so the TOTAL row by work stream is hard-coded or wrong. The forecast also matches neither the MP nor the XLS Fee tab. On the forecast, WS-1 and WS-7 overrun their XLS budgets and WS-7 overruns its MP budget ($490K vs $345K). | n/a (internal error) | Rebuild the forecast from the MP allocations using live formulas. Re-test when the checkpoints (Oct. 2025 and Feb. 2026) will be reached. |
| H-5 | HIGH | Retroactive overage approval | EL §3.3; MP §7.3; OCG §4.3; XLS notes | EL: DGC may approve overages up to 10% retroactively within 15 business days of invoice submission; any unapproved excess becomes a credit. MP: the overage must be reported within 5 business days of month-end. OCG: all overages need advance approval, there is no de minimis exception, and unapproved excess is not payable (not merely credited). | Depends on H-1 | Until H-1 is resolved, get pre-approval for every overage. Align the MP window with the EL (or the reverse) and record an express override of OCG §4.3 if retroactive approval is to survive. |
| H-6 | HIGH | EX-6 / WS-1 gap on non-HX-9000 claims (known open item) | EL §2 EX-6; MP §§3.1, 4.6; EML Jan. 16–31 | The EL carve-back covers claims consolidated into the MDL "or [that] otherwise become part of the proceedings covered by this letter", which is broader than the MP and the emails. The MP says the carve-back authorizes no work until a scope amendment is signed, and WS-1 covers only the MDL "as currently constituted". Giles deferred the mechanism and Layton accepted "real-time" amendment. There is no protocol, no budget and no timeline. Because the EL controls, it arguably authorizes work that the MP forbids. | EL for scope; MP for operation | Agree an expedited protocol for consolidated claims now: notice, an interim spending allowance, and a GC decision deadline, together with a budget reserve. |
| H-7 | HIGH | $20,000 gap in expert / disbursement budget | EL §4.1 and Ex. B; MP §3.3 vs §7.2; XLS Disbursement tab; EML | Rebuttal reserve: $230,000 (MP §3.3) vs $210,000 (XLS). Expert line: $780,000 (EL, MP §3.3, EML) vs $760,000 (MP §7.2, XLS). Disbursement total: $1,350,000 vs $1,330,000. The XLS flags the mismatch itself but does not fix it. EL §12(b) requires GC approval for any change to the disbursement budget. | EL ($780K / $1.35M) | Correct MP §7.2 and the XLS to $780,000 / $1,350,000 with a $230,000 rebuttal reserve. |
| H-8 | HIGH | Contract reviewer cost has no budget home and is classified differently in each document | EL §3.2 and Ex. A note; MP §§3.6, 5.5, 7.2; XLS WS-6; OCG §3.1 | EL: a separate line item outside the blended rates (whether it is a fee or a disbursement is not stated). MP: a disbursement, but not line-itemed, and the $1.35M disbursement budget is fully allocated to other categories. XLS: inside the WS-6 fee budget, which may explain the $870K. So it is unclear whether reviewer spend counts toward the AFB, the monthly cap and the checkpoints. OCG §3.1 also requires each reviewer to be approved individually by name. | EL on rate; classification unresolved | Decide whether reviewer spend is a fee (counting toward the AFB and cap) or a disbursement, add an explicit budget line, and adopt a naming and approval procedure for reviewers. |
| H-9 | HIGH | "Aggregate payments" undefined (success fee) | EL §3.5; MP §7.5; EML Jan. 15–31 | The emails document a live disagreement. Voss and Layton proposed indemnity only, excluding defense costs, ALAE and carrier defense reimbursements. Giles wanted total enterprise cost, including carrier payments. The promised alternative definitions were never sent. Layton confirms the EL went out with the term undefined and asked that it be raised again during Matter Plan drafting. The MP did not address it. Also undecided: whether payments by Fortitude or Ridgeline count, and how the Target Resolution Amount (which covers "all claims") interacts with future consolidated claims (H-6). | EL (term is ambiguous) | Negotiate and sign a definitional amendment covering indemnity, carrier-funded payments, defense costs and ALAE, and the treatment of later-added claims. |
| H-10 | HIGH | Direct communication with carriers | EL §8; MP §3.5 (WS-5 description and item (b)) | The MP authorizes "direct communication" with Fortitude and Ridgeline "on all matters", including coverage positions. EL §8 bars the firm from communicating with the carriers about coverage positions, disputes or allocation without first coordinating with and getting approval from the DGC. | EL | Revise the WS-5 description so that every communication with a carrier about coverage goes through the DGC first. |
| H-11 | HIGH | WS-4 activities conflict with "coordinating counsel only" and EX-4 | R1 §2.1(b), (d) vs §2.1 role clarification, exclusion (iii), §5; MP §3.4 | R1 puts "preparation, review, and submission of VCAP materials to the CPSC" and attendance at CPSC meetings in scope. It also says the firm is coordinating counsel only, that all substantive work is Meridian's, and that firm personnel may not communicate with CPSC staff. A voluntary corrective action plan is closely tied to recall decisions, which EX-4 excludes. | R1 for WS-4, within the EL limits | Restate items (b) and (d) as "support to Meridian". Confirm that VCAP input does not amount to recall advice under EX-4. |
| H-12 | HIGH | Document integrity: the "February 10" MP contains March 28 content | MP cover, revision history, §§1, 2.2, 3.4, 5.6, 7.1, App. A | The MP dated Feb. 10, 2025 refers to the CPSC investigation (Mar. 14, 2025), R1 (Mar. 28), WS-4 and a contingency that was already reduced. It also says "seven (7)" work streams while listing six. The executed original, and the original contingency (implied to be $680,000), cannot be verified. Signature blocks in the EL, MP and R1 copies are blank. | n/a | Obtain the fully executed originals of the EL, the Feb. 10 MP and R1. Keep a clean version history. |
| M-1 | MEDIUM | R1 builds on unconfirmed allocations | R1 §2.2 | R1 draws $320K "from within" the AFB. The only apparent source is the contingency, but no document records the original contingency or the draw, and MP §7.1 requires DGC approval for contingency draws. | MP | Document the contingency draw. |
| M-2 | MEDIUM | WS-2 deduplication vs XLS allocation | MP §3.2; XLS | The MP bills overlapping state/MDL work to WS-1, which supports a smaller WS-2. The XLS raises WS-2 and cuts WS-1 without explanation. | MP | Reconcile as part of H-3. |
| M-3 | MEDIUM | Staffing detail below OCG minimums | EL §5.1 and Ex. A; OCG §§2.1(b), (d), 3.1, 3.2, 6.1 | The OCGs require each timekeeper to be listed by name, classification, year of experience, bar admission, office and rate. The EL lists rates by category only, and junior associates and the second paralegal are unnamed. | Depends on H-1 | Issue a named timekeeper schedule for DGC approval. |
| M-4 | MEDIUM | Unnamed contract reviewers and associates vs OCG categorical approval rule | EL §§3.2, 5.1; OCG §3.1 | OCG §3.1 is "categorical", expressly covers document reviewers, and requires DGC approval before an invoice is submitted. The EL approves only headcount per review wave. | Depends on H-1 | Approve reviewers by name for each wave. |
| M-5 | MEDIUM | Staffing-change approvals conflict | EL §5.2; MP §§5.7(c)–(d), 8.6; OCG §6.1 | EL: associate and paralegal changes must be notified to the DGC. MP: junior associate rotation needs no client notice, and senior associate / Of Counsel substitutions are reported only in the next monthly report. OCG: substitutions of senior team members need written approval, and new timekeepers need approval before invoicing. | EL (at least notice to DGC); OCG may require more | Conform MP §5.7 to require notice to the DGC for rotations and approval for substitutions. |
| M-6 | MEDIUM | Adjusting Voss's 40% time cap | EL §5.1; MP §5.1 | EL: the GC's prior approval is required. MP: adjustable by mutual agreement of the Billing Partner and the "Client". | EL | Conform the MP. |
| M-7 | MEDIUM | Of Counsel substitution vs partner-rate billing | MP §5.7(c); EL §5.2 | Marchetti bills at the Partner rate, but the MP treats Of Counsel substitutions as notice-only. A substitute billing at the Partner rate is arguably a "new partner" addition requiring GC consent. | EL | Clarify. |
| M-8 | MEDIUM | 80% monthly-cap early-warning notice omitted | OCG §4.1; EL; MP; XLS | The OCGs require notice by the 20th of any month in which fees are projected to exceed 80% of the cap ($228,000). The XLS forecasts more than $228K in 14 of 16 months, but neither the EL nor the MP mentions the obligation. | OCG (no conflict) | Add it to the reporting calendar. |
| M-9 | MEDIUM | $10K–$25K disbursement notice | OCG §5.2; MP §7.6; EL §4.2 | The MP says disbursements under $25K need no pre-approval and are only documented on invoices. The OCGs require advance written notice for $10K–$25K. MP reallocation approval ("any") is also stricter than the EL (">$25K"). | OCG (supplements the EL); EL governs reallocation | Conform the MP. |
| M-10 | MEDIUM | EX-1 / EX-2 numbering reversed | EML Jan. 15 and 16 vs EL §2 and MP §4 | In the emails, EX-1 is appellate and EX-2 is class action. The executed documents reverse this. Giles "confirm[ed] EX-1 through EX-6" against the email numbering. | EL | Cite exclusions by name as well as number. Confirm the client accepts the final numbering. |
| M-11 | MEDIUM | Mediation completion deadline | MP §§3.7, 6.1 vs §6.2 chart; XLS | The narrative says Mar. 3, 2026, which is correct (90 days before June 1, 2026). The chart says Feb. 28, 2026 (93 days). The XLS says "Mar. 2026". | MP narrative (formula) | Correct the chart. Diary Feb. 28, 2026 as a conservative internal target. |
| M-12 | MEDIUM | "As currently constituted" also excludes new HX-9000 tag-along actions | MP §3.1; EL §1 | WS-1 excludes later tag-alongs and cross-claims even for HX-9000 claims. This sits uneasily with the EL's grant of "comprehensive defense ... through and including trial" in the MDL. | EL | Clarify that later HX-9000 tag-alongs fall within WS-1. |
| M-13 | MEDIUM | QBR attendance vs OCG two-attorney limit | EL §6; MP §8.3; OCG §6.2 | The EL and MP require Layton and Voss at every QBR, with Sinclair supporting and, under R1, Marchetti for WS-4. That is three or four attorneys. OCG §6.2 caps attendance at two without the DGC's pre-approval. The OCG diversity metrics are also missing from the MP's QBR content list. | OCG (supplements) | Get standing DGC approval. Add diversity metrics to QBRs. |
| M-14 | MEDIUM | Regulatory scope before WS-4 existed | EL §§1, 5.1; MP §5.6; EML Jan. 15–24 | On Feb. 3 the EL authorized Marchetti for a "regulatory response" work stream, but no such work stream or scope category existed until R1. The MP dated Feb. 10 lists WS-4 in her authorization. | EL | Treat R1 as the operative authority for regulatory work; see H-2. |
| M-15 | MEDIUM | Unit of measure for settlement authority not stated | EL §7; MP §§3.7, 8.5 | The tiers ($3M / $6M) do not say whether they apply per plaintiff, per incident or in aggregate. With 55 plaintiffs across two forums and an $8.5M target, the answer determines which approver is needed. | EL (ambiguous) | Clarify in writing. |
| M-16 | MEDIUM | Wind-down fee trigger | EL §9; MP §11 | EL: fees billed "in excess of" $2,000,000. MP: "$2,000,000 or more". The outcome differs at exactly $2M. | EL | Conform the MP. |
| M-17 | MEDIUM | Success fee on termination without cause | EL §9; MP §11 | EL: pro rata share (fees billed ÷ AFB), payable at final resolution. MP: the success fee "remains available", which suggests the full fee. | EL | Conform the MP summary. |
| L-1 | LOW | R1 and XLS cite the wrong EL sections | R1 §§2.2, 3; XLS | R1 cites EL §7.1 (AFB; actually §3.4), §§7.2–7.3 (cap and checkpoints; actually §§3.3–3.4), §8.1 (disbursements; actually §4.1), §8.3 (approval; actually §4.2) and "MP §5.4" for staffing procedures (actually §5.7). The XLS cites "EL §4" for the AFB and "EL §6" for travel. | — | Correct the citations. |
| L-2 | LOW | Exclusion wording differs | EL §2; MP §4 | EX-3: the MP adds contribution, indemnity and supplier claims. EX-4: in-house "legal" team (EL) vs "regulatory affairs" team (MP). EX-5: the MP adds CPSC rulemaking. These do not conflict in substance, but the EL controls. | EL | Harmonize. |
| L-3 | LOW | WS-7 name | R1 §6 | "Settlement Evaluation and Mediation Preparation" vs "Settlement Strategy and Mediation". | MP | Conform. |
| L-4 | LOW | Meridian address | MP §9.1; R1 §2.1 | 1325 G Street NW, Ste 900, DC 20005 vs 1100 Connecticut Ave NW, Ste 800, DC 20036. | — | Verify. |
| L-5 | LOW | Rev. 1 says "Comprehensive Engagement Letter" | R1 §1 | Not the EL's defined term. | — | Conform. |
| L-6 | LOW | Plaintiff counts | EL §1; MP §§1, 2.1, 2.2 | EL: 43 + 7 across "the litigation". MP: 43 + 7 in the MDL plus 5 state-court plaintiffs (55 in total). The incidents injured 7 + 4 = 11 workers, so the 43 individual plaintiffs presumably include derivative claimants. This is not explained. | — | Confirm the plaintiff roster; it affects the success fee and settlement tiers. |
| L-7 | LOW | Giles email domain | EML; MP App. A | rgiles@pinnacleindustrial.com vs rgiles@pinnacleind.com. | — | Verify for notices. |
| L-8 | LOW | Work-stream leads in XLS | XLS vs MP §§3.2, 3.5, 3.6 | XLS: WS-2 led by Voss and Sinclair; WS-5 overseen by Layton; WS-6 led by junior associates and Oduya. MP: Sinclair leads WS-2 and WS-6; WS-5 is Marchetti with a junior associate. | MP | Conform the XLS. |
| L-9 | LOW | Checkpoint report contents | EL §3.4; MP §7.4; OCG §4.2(c) | The OCGs also require a written explanation of any work-stream variance over 10%; the EL and MP omit it. | OCG (supplements) | Add to the report template. |
| L-10 | LOW | New-expert procedure details | EL §4.2; MP §8.4; OCG §5.3 | The OCGs add 15 business days' advance notice, a CV, and certification of expert invoices. | OCG (supplements) | Add to the WS-3 protocol. |
| L-11 | LOW | Monthly report horizon | MP §8.2(e); OCG §7.1(b) | The MP covers deadlines 30–60 days out; the OCGs require 30, 60 and 90 days. | OCG | Conform. |
| L-12 | LOW | Mediator approval delegation | EL §7; MP §3.7; EML Jan. 20 | Giles said he could approve "on [Meg's] behalf". The EL and MP require joint approval by the GC and Voss, with no delegation. | EL | Confirm whether delegation was intended. |
| L-13 | LOW | Budget runs only "through conclusion of trial" | EL §3.4; MP §3.1(f); XLS | WS-1 includes post-trial motions, but the AFB runs only to the end of trial. The XLS allots just $140K to the trial month. | EL | Plan a post-trial budget amendment. |

# 5. Budget Reconciliation Detail

## 5.1 Fee budget by work stream

| Work stream | MP §7.1 | XLS Fee tab | XLS Forecast (column sum) | XLS Forecast (stated TOTAL) | Variance MP vs XLS |
| --- | --- | --- | --- | --- | --- |
| WS-1 Federal MDL | $1,850,000 | $1,650,000 | $1,750,000 | $1,650,000 | ($200,000) |
| WS-2 State Court | $475,000 | $480,000 | $460,000 | $480,000 | $5,000 |
| WS-3 Expert Mgmt | $385,000 | $385,000 | $385,000 | $385,000 | — |
| WS-4 CPSC | $320,000 | $320,000 | $300,000 | $320,000 | — |
| WS-5 Insurance | $95,000 | $95,000 | $95,000 | $95,000 | — |
| WS-6 E-Discovery | $420,000 | $870,000 | $770,000 | $870,000 | $450,000 |
| WS-7 Settlement | $345,000 | $450,000 | $490,000 | $450,000 | $105,000 |
| Contingency | $360,000 | — | — | — | ($360,000) |
| Total | $4,250,000 | $4,250,000 | $4,250,000 | $4,250,000 | — |

## 5.2 Disbursement budget

| Category | EL §4.1 / Ex. B | MP §3.3 text | MP §7.2 table | XLS |
| --- | --- | --- | --- | --- |
| Expert witness fees | $780,000 | $780,000 ($550K named + $230K reserve) | $760,000 | $760,000 ($550K + $210K reserve) |
| E-discovery (Precept) | $340,000 | — | $340,000 | $340,000 |
| Travel and deposition | $155,000 | — | $155,000 | $155,000 |
| Court reporting | $75,000 | — | $75,000 | $75,000 |
| Contract reviewers | Separate line item (no amount) | — | "Within the disbursement framework" (no amount) | Inside WS-6 fees |
| Total | $1,350,000 | — | $1,330,000 | $1,330,000 |

## 5.3 Figures checked and consistent

The following were recomputed and agree across every document that states them: 5% of AFB = $212,500; 50% and 75% checkpoints = $2,125,000 and $3,187,500; monthly cap overage ceiling = $313,500 (10% = $28,500); success fee example = 7.5% × $2.5M = $187,500; wind-down fee example = 2% × $2.5M = $50,000; EL Ex. B total $4.25M + $1.35M = $5.6M; named experts = $550,000; MP §7.1 and XLS fee totals = $4,250,000; XLS monthly totals and cumulative figures (50% reached Oct. 2025 at $2,142,000; 75% reached Feb. 2026 at $3,268,000); WS-4 internal allocation ($120K + $80K + $70K + $50K = $320K).

# 6. Recommended Priority Actions

1. Get the GC's written re-approval ratifying WS-4 ($320K > $212,500), and confirm no WS-4 fees were billed before it (H-2).

2. Sign an EL amendment or side letter that (a) defines "aggregate payments" (H-9); (b) lists each OCG provision the EL overrides by section number (H-1, H-5, M-3 to M-5); (c) sets a protocol for non-HX-9000 and tag-along consolidation (H-6, M-12); and (d) states the unit of measure for settlement authority (M-15).

3. Reissue a conformed MP (Revision 2) that: corrects §7.2 to $780K / $1.35M; fixes the WS-5 carrier-communication language, the mediation chart date, staffing-change rules, the Voss cap, and the termination summaries; adds a contract reviewer budget line; and corrects citations.

4. Rebuild the budget workbook from MP §7.1 using live formulas, and document any DGC-approved transfers or contingency draws (H-3, H-4, H-7, H-8).

5. Obtain the fully executed originals of the EL, the original Feb. 10 MP and R1, and file them in the matter records (H-12).

6. Update the compliance calendar for OCG-only obligations: the 80% cap notice by the 20th, $10K–$25K disbursement notices, 30/60/90-day reporting, diversity metrics, and QBR attendance approval (M-8, M-9, M-13, L-9 to L-11).

This report reflects only the six documents provided. Where the report says a document "controls", that is our reading of the hierarchy clauses, not a legal opinion on enforceability.