INVOICE COMPLIANCE DEVIATION REPORT

Blackwell Stanhope LLP Invoice No. BS-VIH-2024-1031 (October 1–31, 2024)
Clearwater Technologies, Inc. v. Saxonbrook Industrial Holdings, Inc., No. 1:23-cv-00847 (N.D. Ill.)

| Field | Detail |
| --- | --- |
| Prepared for | Daniel Okafor, Associate General Counsel (Designated Contact); cc: Margaret Chen-Watkins, General Counsel |
| Invoice reviewed | BS-VIH-2024-1031, dated November 4, 2024; transmitted by S. Messina email of November 4, 2024 |
| Invoice total as stated | $487,329.14 (Fees $242,687.00; Expenses $244,642.14) |
| Governing standards | VIH Outside Counsel Billing Guidelines v4.2 (eff. 1/1/2024; accepted by firm 1/18/2024); Engagement Letter and Exhibits A–B; VIH Prior Approval Log (current as of 11/1/2024) |
| Overall conclusion | NON-COMPLIANT. Return the invoice for correction under §8.1 and §11.2(f). The payment clock under §8.1 does not start until a compliant invoice is received. |

# 1. Executive Summary

We checked every one of the 139 fee entries and 22 expense lines in the invoice against the Billing Guidelines, the Engagement Letter, the Exhibit A rate schedule, the Exhibit B expert approvals, the Prior Approval Log and the transmittal email. The invoice has serious problems at three levels:

Internal arithmetic does not reconcile. The fee line items add up to $269,554.00 (743.8 hours). The invoice states fees of $242,687.00 (671.8 hours). The expense lines add up to $244,652.14, not the stated $244,642.14. Together the line items total $514,206.14, which is $26,877.00 more than the stated invoice total. Seven of the eight timekeeper subtotals are understated. Because the invoice does not reconcile, it cannot be processed as submitted.

Charges billed without the required approval, or that can never be billed. Several charges required prior approval and have none: an unapproved summer associate; contract-attorney time billed after the approval expired; San Francisco travel outside the Litigation Forum; a $48,250 e-discovery vendor; local counsel; and firm overhead charges that the Guidelines prohibit outright.

Invoice-level and format failures. The invoice exceeds $350,000 but no written explanation was provided (§10.1). Cumulative 2024 spend has passed the 75% budget threshold ($2,100,000) with no notification. Every entry uses UTBMS task codes (L510–L550) that are not on the approved list in Appendix A. 138 of 139 narratives are shorter than the 30-word minimum.

Recommended financial disposition (calculated from the line-item detail, which is the only itemised basis available):

| Component | Fees | Expenses | Total |
| --- | --- | --- | --- |
| Line-item detail as billed | $269,554.00 | $244,652.14 | $514,206.14 |
| Recommended disallowance / reduction | ($83,431.45) | ($73,221.34) | ($156,652.79) |
| Withheld pending documentation | — | ($150,612.04) | ($150,612.04) |
| Currently supportable (payable as undisputed once corrected invoice received) | $186,122.55 | $20,818.76 | $206,941.31 |
| Maximum potentially payable if all withheld items are substantiated | $186,122.55 | $171,430.80 | $357,553.35 |

Payment should never exceed the stated invoice total of $487,329.14, even though the line items add up to more. The firm must say which figure is correct. It must also recalculate the 2% "technology surcharge," which it computed on the understated fee figure; that surcharge is disallowed in any event. Separately, §7.3 says an invoice containing disbursement markups "will be returned for correction." The photocopy rate and the surcharges trigger that provision.

Discretionary items, which are not included in the figures above: another $14,875.00 of fees shows signs of duplicative or excessive staffing (§4.3(f), §5.2). These entries are listed in Section 5 for the Designated Contact to decide on.

# 2. Scope, Sources and Method

| Document | Use in review |
| --- | --- |
| VIH Outside Counsel Billing Guidelines v4.2 | Primary standard (controls over engagement letter per §1.2 and Engagement Letter §4) |
| Engagement Letter (Mar. 15, 2023) incl. Exhibit A (2024 rates) and Exhibit B (experts) | Approved timekeepers, rates, budget ($2.8M), 75%/$350K triggers, prior-approval list |
| VIH Prior Approval Log (as of Nov. 1, 2024) | Official record of approvals PA-001 to PA-006; confirms "No additional approval requests are currently pending" |
| Invoice workbook (Summary, Fees Detail, Expenses, Timekeeper Summary, Matter Status, LEDES Export, Rate Schedule, YTD) | Line-by-line testing; arithmetic recomputation; LEDES field checks |
| Transmittal email (S. Messina, Nov. 4, 2024) | Status summary, representations, required §10.1 disclosures |

Method: (1) We recalculated every fee line (hours × rate) and every subtotal. (2) We matched each timekeeper and rate to Exhibit A and the approval log. (3) We tested every entry for task codes, block billing, the 30-word minimum, prohibited categories and staffing caps. (4) We tested every expense for rate caps, the prohibited-expense list, prior approval and documentation. (5) We checked invoice-level requirements under §8 and §10. We applied the adjustments in a fixed order so that nothing is reduced twice: first whole-entry disallowances, then caps, then the 30% block-billing reduction on the entries that remain.

# 3. Deviation Register (Summary)

| ID | Severity | Category | Deviation | Amount | Authority | Action |
| --- | --- | --- | --- | --- | --- | --- |
| D-1 | Critical | Arithmetic | Fee subtotals/total and expense total do not reconcile to line items | Line items $514,206.14 vs. stated $487,329.14 | §8.1(d),(f); App. B | Return for correction |
| D-2 | Critical | Unapproved timekeeper | Summer associate Timothy Kwan — 8 entries, 34.5 hrs | ($10,177.50) | §3.1; EL §2; Ex. A n.4 | Disallow in full |
| D-3 | Critical | Expired approval | Contract attorney Elaine Cho — 21 entries, 214.0 hrs after 9/30/2024 expiry | ($41,730.00) | §3.1; §9.1(6); PA-005 | Disallow in full |
| D-4 | High | Deposition staffing | 3rd/4th attorneys at Torres (10/15) and Nakamura (10/24) depositions | ($5,660.00) | §5.1 | Disallow |
| D-5 | High | Internal conference | 10/28 conference: 5 attorneys, 19.0 attorney-hrs (cap 4 attendees / 4 attorney-hrs) | ($6,216.00) plus Kwan in D-2 | §5.1 | Reduce to cap |
| D-6 | High | Unapproved travel | San Francisco travel (outside Litigation Forum) — travel time billed at 100% rate | ($6,174.00) | §9.1(3); §6.1 | Disallow (alt.: 50%) |
| D-7 | High | Travel expenses | Airfare, hotel $489/night, meals over cap, black car | ($7,234.00) | §9.1(3); §6.1 | Disallow (alt. schedule §4.4) |
| D-8 | Medium | Prohibited time | Billing/invoice preparation and file organization (entries 125, 133, 139) | ($2,715.50) | §4.3(a),(b) | Disallow |
| D-9 | Medium | Block billing | 10 entries combining distinct tasks — 30% reduction | ($10,758.45) | §4.2 | Reduce 30% |
| D-10 | High | Unapproved vendor | Forrest Data Solutions $48,250 — no approval; >$10,000 | ($48,250.00) | §9.1(2),(7); §7.1(c) | Disallow |
| D-11 | High | Unapproved local counsel | Brixton & Associates retainer | ($1,500.00) | §9.1(5); EL §8(5) | Disallow |
| D-12 | High | Prohibited overhead | Technology surcharge (2%) and after-hours word processing | ($7,198.74) | §7.1(a),(b),(d); §7.3 | Disallow |
| D-13 | Medium | Rate cap | Photocopying at $0.25/page vs $0.15 cap (48,200 pp.) | ($4,820.00) | §7.1; §7.3; EL §5 | Reduce |
| D-14 | Medium | Monthly cap | Westlaw $4,218.60 vs $3,500 monthly cap | ($718.60) | §7.1 | Reduce |
| D-15 | Medium | Approval scope / hosting | Relativity hosting $18,500 — vendor unidentified; exceeds PA-004 estimate | ($3,500.00) + $15,000 withheld | §7.1(c); §9.1; PA-004 | Reduce / withhold |
| D-16 | Medium | Documentation | Expert fees (Voss, Huang) without expert invoices; courier charges unitemized | $130,372.04 withheld | §7.1; §7.2; Ex. B | Withhold |
| D-17 | Medium | Approval scope | Torres transcript $5,240 (> $5,000; expedited; post-fact-discovery) | $5,240.00 withheld | §7.1; PA-003 | Withhold |
| D-18 | High | Budget notice | 75% threshold crossed ($2.23M+) with no written notification | — | §10.1; EL §7 | Require notice & revised budget |
| D-19 | High | Monthly threshold | Invoice > $350,000 without written explanation | — | §10.1; EL §7 | Require explanation |
| D-20 | High | LEDES/UTBMS | All 139 entries use L510–L550 codes not in Appendix A; activity/expense codes misapplied; LEDES narratives truncated; no TIMEKEEPER_NAME field | — | §4.4; §8.1; App. A–B | Return for correction |
| D-21 | Medium | Narrative detail | 138 of 139 narratives under 30 words (LEDES version: 139 of 139) | — | §4.1 | Resubmit with detail |
| D-22 | Low–Med | Transmittal/status accuracy | Email omits two depositions and all non-compliant items; filing status inconsistent with time entries | — | §8.1(g); §1.2 | Clarify |

# 4. Detailed Findings

## 4.1 Invoice arithmetic and integrity (D-1)

| Timekeeper | Stated hrs | Stated fees | Line-item hrs | Line-item fees | Variance |
| --- | --- | --- | --- | --- | --- |
| Sandra Messina | 47.3 | $42,333.50 | 51.6 | $46,182.00 | $3,848.50 |
| Jonathan Pryor-Hall | 112.6 | $64,745.00 | 125.1 | $71,932.50 | $7,187.50 |
| Rebecca Tanaka | 96.4 | $40,970.00 | 117.3 | $49,852.50 | $8,882.50 |
| Marcus DeVries | 78.2 | $25,415.00 | 80.2 | $26,065.00 | $650.00 |
| Timothy Kwan | 34.5 | $10,177.50 | 34.5 | $10,177.50 | $0.00 |
| Elaine Cho | 186.0 | $36,270.00 | 214.0 | $41,730.00 | $5,460.00 |
| Nathaniel Briggs | 64.8 | $12,636.00 | 67.6 | $13,182.00 | $546.00 |
| Alicia Rosenberg | 52.0 | $10,140.00 | 53.5 | $10,432.50 | $292.50 |
| TOTAL | 671.8 | $242,687.00 | 743.8 | $269,554.00 | $26,867.00 |

Individual lines are correct. Every line is correct on its own (hours × rate = amount, with no variance). The mistakes are all in the subtotals. Only Timothy Kwan's subtotal matches his entries.

Expenses. The 22 expense lines add up to $244,652.14, compared with the stated $244,642.14 (a difference of $10.00).

LEDES. The LEDES export carries an INVOICE_TOTAL of $487,329.14, but its LINE_ITEM_TOTAL fields add up to $514,206.14. A LEDES file in that state will fail validation in an e-billing system.

Knock-on effect. The YTD Summary adds the understated October figure, so it reports cumulative spend of $2,230,941.14 (79.7%). On the line-item figures, cumulative spend is $2,257,818.14 (80.6%).

Payment terms. The Summary sheet shows a payment due date of December 5, 2024 on "Net 30" terms. Under §8.1 and Engagement Letter §6, the 30 days run only from receipt of a compliant invoice, so no due date applies yet.

## 4.2 Timekeeper approval (D-2, D-3)

D-2 — Timothy Kwan (Summer Associate, TK006, $295/hr).

Kwan is not on Exhibit A or in the Prior Approval Log. §3.1 says summer associates "are not billable to VIH matters without prior written approval," and that time from non-approved timekeepers "will be disallowed in their entirety without exception." Engagement Letter §2 and Exhibit A note 4 say the same. The invoice's own Rate Schedule tab lists him as "N/A — Law Student" with an effective date of 10/01/2024, but no approval exists and the log confirms that no request is pending. Entries 58, 70, 78, 84, 97, 109, 116 and 130 (34.5 hrs) → disallow $10,177.50. His research also overlaps with work billed by M. DeVries (e.g., entries 4 and 10 against 58 and 70 on trade-secret identification standards), which is duplicative under §4.3(f) in any case.

D-3 — Elaine Cho (Contract Attorney, EC005, $195/hr).

Approval PA-005 and Exhibit A cover July 22 to September 30, 2024 only. The log quotes the approval directly: "This approval expires on September 30, 2024. Any extension … requires a new written approval request." No renewal was requested. Under §9.1(6), failure to renew "will result in disallowance of all time billed after the expiration date." All 21 October entries (214.0 hrs) → disallow $41,730.00. The invoice subtotal shows only 186.0 hrs / $36,270.00, which understates her time. The invoice Rate Schedule gives an effective date of 07/22/2024 but omits the expiry date. Cho also billed 9.0–9.5 hours every working day, and PA-005 estimated 400–500 hours in total. VIH should ask for her cumulative July–September hours to confirm the estimate was not already exceeded.

## 4.3 Staffing restrictions (D-4, D-5)

D-4 — Depositions (maximum two attorneys, §5.1).

| Deposition | Attorneys billing attendance | Allowed | Disallowed entries | Amount |
| --- | --- | --- | --- | --- |
| Michael Torres (10/15) | Messina (61), Pryor-Hall (62), Tanaka (63), DeVries — "monitor remotely" (64) | Messina, Pryor-Hall | 63 Tanaka 7.2h; 64 DeVries 4.0h | $4,360.00 |
| Sarah Lindgren (10/18) | Pryor-Hall (76), Tanaka (77) | Both | — | $0.00 |
| David Nakamura (10/24) | Pryor-Hall (100), Tanaka (101), DeVries — "monitor" (102) | Pryor-Hall, Tanaka | 102 DeVries 4.0h | $1,300.00 |
| Total |  |  |  | $5,660.00 |

Remote monitoring counts as attendance: the attorney is present at the deposition and billing for it. No prior approval for extraordinary circumstances was sought. Paralegal attendance (entries 66, 80 and 104) is not subject to the attorney cap and is not adjusted here.

D-5 — October 28 internal strategy conference.

Five attorneys attended (Messina, Pryor-Hall, Tanaka, DeVries, Kwan), each billing 3.8 hours, for 19.0 attorney-hours in total. This breaks both independent limits in §5.1: the 4-attendee cap and the 4 attorney-hour cap. Kwan's entry (116) is already disallowed under D-2 and also as the fifth attendee. The remaining 15.2 hours ($8,436.00) are reduced to 4.0 attorney-hours, allocated pro rata by value, which allows $2,220.00 and reduces the charge by $6,216.00. The transmittal email presents this conference as routine and does not disclose that it exceeded the caps.

## 4.4 Travel (D-6, D-7)

San Francisco is outside the Litigation Forum, which §2 defines as Cook County and the five collar counties. §9.1(3) and Engagement Letter §8(3) therefore required prior written approval, with a request covering destination, purpose, duration and estimated costs. None appears in the log. PA-006 approved only "subpoena service, compliance negotiation, and related filing fees" for Nexon, capped at $5,000; it did not approve attorney travel. Primary recommendation: disallow the travel time ($6,174.00) and all travel expenses ($7,234.00) under §9.3(a). Retroactive approval is available only in "extraordinary circumstances" (§9.3(b)).

Even if VIH were to grant retroactive approval, the following deviations would remain:

| Line | Item | Billed | Compliant | Reduction | Basis |
| --- | --- | --- | --- | --- | --- |
| Fee 25 | Messina travel 4.2h @ $895 (full rate) | $3,759.00 | $1,879.50 | $1,879.50 | §6.1 — 50% of rate |
| Fee 26 | Pryor-Hall travel 4.2h @ $575 (full rate) | $2,415.00 | $1,207.50 | $1,207.50 | §6.1 — 50% of rate |
| E-008 | Messina business-class airfare ORD–SFO | $2,847.00 | Verify | Verify | §6.1(a)–(b): business class is allowed only if the scheduled flight is 4+ hours. ORD–SFO is typically scheduled at about 4h15m–4h45m, so it may qualify. Ask for the itinerary; if under 4 hours, reduce to the economy fare (Pryor-Hall paid $412). |
| E-009 / E-013 | Hotel $489/night × 3 × 2 travelers | $2,934.00 | $1,950.00 | $984.00 | §6.1 — $325/night cap. A third night (10/9) is questionable because the inspection ended 10/9 and no return travel was billed |
| E-010 | Messina meals $312.40 / 3 days | $312.40 | $225.00 | $87.40 | §6.1 — $75/person/day; itemized receipts; no alcohol |
| E-014 | Pryor-Hall meals $198.40 | $198.40 | $198.40 | $0.00 | Within cap; receipts required |
| E-011 | Messina black car service | $387.00 | $0.00 | $387.00 | §6.1 — never reimbursable |
| E-015 | Pryor-Hall ride-share | $143.20 | $143.20 | $0.00 | Permitted with receipts |

Under this alternative, travel time would be reduced by $3,087.00 and expenses by $1,458.40, before any airfare adjustment. Having both the lead partner and the senior associate attend a document inspection should also be questioned (§5.2). See Section 5.

## 4.5 Time-entry requirements (D-8, D-9, D-20, D-21)

D-8 — Prohibited time (§4.3(a)–(b)).

| Entry | Timekeeper | Narrative (excerpt) | Amount | Reason |
| --- | --- | --- | --- | --- |
| 133 | Messina 1.4h | Review monthly billing summary and matter status report; conference call with Howard Blackwell regarding matter budget status | $1,253.00 | Invoice review and internal budget administration (§4.3(a),(b)) |
| 125 | Rosenberg 3.5h | … prepare materials for month-end billing reconciliation | $682.50 | Billing preparation; not separated from other work, so disallowed in full |
| 139 | Rosenberg 4.0h | … prepare month-end billing support documentation and file organization | $780.00 | Billing preparation and file organization |

D-9 — Block billing (§4.2; 30% reduction, $10,758.45).

| Entry | Timekeeper | Hrs | Narrative | Billed | 30% reduction |
| --- | --- | --- | --- | --- | --- |
| 8 | Jonathan Pryor-Hall | 4.8 | Continue analysis of Clearwater supplemental privilege log; draft challenge letter to opposing counsel regarding entries 912, 978, 1,034, and 1,101 wh | $2,760.00 | $828.00 |
| 14 | Sandra Messina | 5.8 | Review and analyze expert report materials; conference with J. Pryce-Hall and R. Tanaka regarding expert discovery strategy and deposition preparation | $5,191.00 | $1,557.30 |
| 44 | Jonathan Pryor-Hall | 3.8 | Debrief with S. Messina on Nexon Semiconductor document inspection results; prepare summary memorandum of key findings and recommended follow-up actio | $2,185.00 | $655.50 |
| 49 | Sandra Messina | 2.0 | Conference with J. Pryce-Hall regarding final deposition strategy for Michael Torres; review revised deposition outline. | $1,790.00 | $537.00 |
| 54 | Sandra Messina | 2.8 | Final preparation for Michael Torres deposition; review key documents and deposition outline; conference call with client representative Daniel Okafor | $2,506.00 | $751.80 |
| 61 | Sandra Messina | 9.3 | Prepare for and attend deposition of Michael Torres (former Clearwater engineer); post-deposition debrief with team. | $8,323.50 | $2,497.05 |
| 62 | Jonathan Pryor-Hall | 8.7 | Prepare for and attend deposition of Michael Torres; coordinate exhibits and manage real-time document review during examination. | $5,002.50 | $1,500.75 |
| 88 | Jonathan Pryor-Hall | 7.4 | Draft motion for protective order regarding Clearwater's expert discovery requests; research applicable standards; draft supporting memorandum; compil | $4,255.00 | $1,276.50 |
| 105 | Sandra Messina | 2.5 | Review David Nakamura deposition transcript; conference call with client representative Daniel Okafor regarding deposition outcomes and litigation str | $2,237.50 | $671.25 |
| 126 | Sandra Messina | 1.8 | Final review and approval of motion for protective order prior to filing; conference with J. Pryce-Hall on filing strategy. | $1,611.00 | $483.30 |

These ten entries combine clearly different activities in a single time allocation: conferences or client calls with drafting or review, preparation with attendance and a debrief, or drafting with research, exhibit compilation and case review. More than 100 other entries join tasks with semicolons (e.g., "review …; prepare memorandum"). They are not reduced here, but the firm should be told to break them out on resubmission. Repeat violations support the further remedies in §4.2.

D-20 — LEDES/UTBMS coding (§4.4, §8.1, Appendices A–B).

Task codes. Appendix A approves litigation codes L110–L190 only. All 139 fee entries use L510, L520, L530, L540 or L550, which are not on that list. In the standard UTBMS litigation code set, the L500 series is the Appeal phase, which misdescribes the work. For example, discovery work should be L130 and expert work L140.

Activity codes. Activity codes appear to be misapplied against the standard UTBMS set. Deposition and inspection attendance is coded A104 (Review/Analyze), not A109 (Appear/Attend). Internal conferences are coded A106 (Communicate with client). Research is coded A101 (Plan and prepare), not A102. Travel is coded A107.

Expense codes. Measured against the standard UTBMS expense codes, most codes do not fit the charge. Airfare is coded E101 (which is copying), transcripts E107, Westlaw E108, experts E112 and local counsel E115. The standard codes would be E110 for out-of-town travel, E115 for transcripts, E106 for online research, E119 for experts and E122 for local counsel. Appendix A does not reproduce expense codes, so this item should be confirmed with VIH's e-billing administrator.

Field set and narratives. The LEDES export has no TIMEKEEPER_NAME field, which Appendix B requires. Its narratives are shortened versions of the Excel narratives (for example, entry 2 drops the recommendations, and entry 32 drops the list of documents reviewed). The two versions of the invoice are therefore not the same. The email says a separate LEDES 1998B flat file was attached, but only the Excel export was in the materials reviewed. VIH should confirm what it actually received.

D-21 — Narrative length (§4.1).

138 of 139 Excel narratives are under the 30-word minimum; only entry 8 has more than 30 words (32). The median is 18 words, and the shortest entries (travel entries 25 and 26, and 104) have 11. Every LEDES narrative is under 30 words. Some entries are also generic by the standard of §4.1, e.g., 136 ("Finalize October research memoranda; update case law research binder"), 121, 89 and 73 ("Continue technical document review and analysis"). No separate dollar reduction is applied here, but VIH may reduce or disallow entries that lack enough detail (§4.1), and the firm should resubmit with full narratives.

## 4.6 Expenses and prior approvals (D-10 to D-17)

| Line | Description | Billed | Action | Adjustment / Hold | Analysis |
| --- | --- | --- | --- | --- | --- |
| E-001 | Dr. Voss — October | $87,500.00 | Withhold | $87,500.00 | Approved (PA-001; cap $150,000). §7.1 requires the expert's own invoice with every invoice that includes expert charges, and none was provided. $87,500 is 140 hours at $625/hr in one month. Ask for cumulative billings to date to confirm the cap is not exceeded (Ex. B requires re-authorisation before any overage). |
| E-002 | Prof. Huang — October | $42,000.00 | Withhold | $42,000.00 | Approved (PA-002; cap $100,000; $550/hr, about 76.4 hrs). Expert invoice and cumulative-to-date figures required. |
| E-003 | Torres transcript (expedited) | $5,240.00 | Withhold | $5,240.00 | Over the $5,000 single-deposition pre-approval threshold. PA-003 covers "fact discovery depositions," but fact discovery closed 9/15/2024. Confirm the deposition falls within PA-003 (and was authorised by stipulation or court order), justify the expedited premium, and supply the cumulative amount against the $65,000 estimate. Receipt required. |
| E-004 / E-005 | Lindgren / Nakamura transcripts | $9,632.50 | Allow* | — | Each under $5,000. *Subject to vendor invoice and the same PA-003 scope confirmation. |
| E-006 | Westlaw | $4,218.60 | Reduce | $718.60 | Capped at $3,500 per month per matter (§7.1); no approval for excess. |
| E-007 | In-house copying 48,200 pp @ $0.25 | $12,050.00 | Reduce | $4,820.00 | Capped at $0.15/page, so $7,230. The excess is a markup (§7.3). Large-volume copying should be outsourced, and the volume is doubtful given electronic review. |
| E-008–E-015 | SF travel | $7,234.00 | Disallow | $7,234.00 | No out-of-forum travel approval (see §4.4). |
| E-016 | Courier — "various" | $872.04 | Withhold | $872.04 | Not itemised; §7.2 requires vendor invoices. |
| E-017 | Relativity hosting | $18,500.00 | Reduce + withhold | $3,500.00 + $15,000.00 withheld | PA-004 approved hosting through third-party vendor CloudStar Technologies at an estimated $12–15K/month. The invoice does not name the vendor. If this is a firm-internal platform, it is not reimbursable at all (§7.1(c)). Amount above the approved range is disallowed. The balance is withheld pending the CloudStar invoice and confirmation that the Phase II review phase is still ongoing. |
| E-018 | After-hours word processing / admin | $2,345.00 | Disallow | $2,345.00 | §7.1(a),(d); Engagement Letter §5. |
| E-019 | Technology surcharge 2% | $4,853.74 | Disallow | $4,853.74 | §7.1(b); §7.3 (surcharge prohibited). |
| E-020 | Forrest Data Solutions | $48,250.00 | Disallow | $48,250.00 | A single expense over $10,000 and a vendor over $10,000 require prior approval (§9.1(2),(7)); none in the log. The vendor is not the approved CloudStar, and the charge includes "hosting." Fee entries 37 and 39 show the vendor was engaged during the trip on 10/8–10/9 without a request. |
| E-021 | Brixton & Associates (local counsel, SF) | $1,500.00 | Disallow | $1,500.00 | Engaging local counsel requires prior approval with firm, attorney, rates and scope (§9.1(5); EL §8(5)). None in the log. Also ask whether Brixton has billed or will bill more. |
| E-022 | Filing fees / service of process | $456.26 | Allow* | — | No approval required. *Receipts required; Nexon service costs fall within PA-006 ($5,000). |

## 4.7 Budget and invoice-level requirements (D-18, D-19)

75% threshold (D-18). Cumulative 2024 spend through September was $1,743,612.00 (62.3%). October takes it to $2,230,941.14 on the firm's figures or $2,257,818.14 on the line items. Either way it is above the $2,100,000 threshold, which triggers the §10.1 / Engagement Letter §7 requirement to give written notice within 5 business days, with a summary of work, the remaining tasks and a revised estimate for the year. The transmittal email and the Matter Status tab give a utilisation figure (79.7%) but no notice, no description of remaining work and no revised budget.

Budget trajectory. This invoice is more than twice the 2024 monthly average of about $193,700. With $569,058.86 remaining on the firm's own figures, and expert reports due December 20, 2024, the matter is likely to overrun the budget. An overrun of more than 10% ($280,000) requires a meeting between the lead partner and the General Counsel (§10.1). VIH should ask for a November–December forecast now.

$350,000 monthly threshold (D-19). Any invoice over $350,000 must be accompanied by a written explanation of the cost drivers, why the work was necessary and the expected spending trajectory. None was provided. The email simply states the total.

Timing / status summary. The invoice was submitted on November 4, within 45 days of month-end (compliant). The Matter Status tab includes upcoming deadlines (compliant in form, but see D-22 on accuracy).

## 4.8 Transmittal email and status-summary accuracy (D-22)

Omitted depositions. The email mentions only the Torres deposition. The Matter Status tab and the time entries show that the Lindgren (10/18) and Nakamura (10/24) depositions were also taken.

Motion filing status. The email says the protective-order motion will be filed "in early November." Entries 124 ("coordinate electronic filing with court clerk"), 120 ("prepare final filing package") and 126 ("Final review … prior to filing") suggest it was filed in October. The firm should confirm the filing status. If the motion has not been filed, entry 124 should be revisited.

Non-disclosure. The email does not mention the summer associate, the expired contract-attorney approval, the Forrest vendor, local counsel, or the fact that San Francisco travel had not been approved. It justifies two attorneys at the inspection "to ensure a comprehensive review" but does not refer to any approval. Under §1.2, submitting an invoice is a representation that it complies with the Guidelines.

Name inconsistency. The narratives spell the senior associate's name "Pryce-Hall," and so does the cc email address (jprycehall@). Exhibit A and the timekeeper records use "Pryor-Hall." The firm should confirm the timekeeper identity for the LEDES record.

Post-close fact discovery. Fact discovery closed September 15, 2024, but three fact-witness depositions and a third-party document inspection took place in October. The firm should confirm the authority for this (stipulation or court order), because it affects the scope of PA-003 and PA-006.

# 5. Discretionary Review Items (not included in recommended totals)

| Entries | Issue | Amount at issue | Authority | Suggested position |
| --- | --- | --- | --- | --- |
| 33, 39 | Second attorney (Pryor-Hall) at the Nexon document inspection alongside the lead partner; review and cataloguing could have been done by one attorney or a more junior one | $7,762.50 | §4.3(f); §5.2 | Ask for justification; consider disallowing |
| 68, 69 | Tanaka and DeVries each reviewed the Torres transcript, in addition to Pryor-Hall's summary (67) | $3,147.50 | §4.3(f) | Consider disallowing as duplicative |
| 108 | DeVries reviewed the Nakamura transcript, in addition to Messina (105) and Pryor-Hall (106) | $1,365.00 | §4.3(f) | Consider disallowing |
| 46 | "Supplemental" research memo on the same topic as entry 22 (permissible deposition topics for former employees) | $1,137.50 | §4.3(f) | Request work product / justification |
| 138 | "Archive completed deposition materials" and month-end reports — administrative | $780.00 | §4.3(b) | Consider disallowing |
| 124 | Filing coordination, if the motion was not in fact filed in October | $682.50 | §4.3(c) | Depends on filing status |
| Total |  | $14,875.00 |  |  |

Other staffing observations: five timekeepers billed about 60 hours preparing for the Torres deposition. The lead partner billed routine items such as reviewing the case management order (entry 1, 1.5h). Deposition preparation entries at several levels overlap (e.g., DeVries 57 and Tanaka 51 both prepared a "deposition summary template"). VIH may reclassify or reduce these under §5.2.

# 6. Items Tested and Found Compliant

All billed rates for approved timekeepers (Messina $895, Pryor-Hall $575, Tanaka $425, DeVries $325, Briggs $195, Rosenberg $195) match Exhibit A and the approval log. No retroactive rate increases.

All time is recorded in 0.1-hour increments.

The motion for protective order is not dispositive, so no §9.1(4) approval was required. No dispositive motion or appeal was billed.

Expert retentions (Voss, Huang) were pre-approved at stated rates. Billing is subject to documentation and cap monitoring (D-16).

Lindgren deposition staffing (two attorneys) is within §5.1.

Pryor-Hall economy airfare, ride-share and meals are within policy (the travel itself was unapproved).

The invoice was submitted within 45 days. It includes the invoice number and date, matter name, case number, billing period and a matter status summary.

# 7. Recommended Adjustment Schedule

| Ref | Adjustment | Type | Amount |
| --- | --- | --- | --- |
| D-2 | Kwan — all entries | Fees | $10,177.50 |
| D-3 | Cho — all entries (post-expiry) | Fees | $41,730.00 |
| D-4 | Deposition excess attorneys (63, 64, 102) | Fees | $5,660.00 |
| D-5 | 10/28 conference reduced to 4 attorney-hrs (112–115) | Fees | $6,216.00 |
| D-6 | Unapproved travel time (25, 26) | Fees | $6,174.00 |
| D-8 | Billing/admin time (125, 133, 139) | Fees | $2,715.50 |
| D-9 | Block billing 30% (10 entries) | Fees | $10,758.45 |
|  | Subtotal — fees |  | $83,431.45 |
| D-7 | SF travel expenses (E-008–E-015) | Expenses | $7,234.00 |
| D-10 | Forrest Data Solutions (E-020) | Expenses | $48,250.00 |
| D-11 | Local counsel (E-021) | Expenses | $1,500.00 |
| D-12 | Admin support + tech surcharge (E-018, E-019) | Expenses | $7,198.74 |
| D-13 | Copying excess (E-007) | Expenses | $4,820.00 |
| D-14 | Westlaw excess (E-006) | Expenses | $718.60 |
| D-15 | Relativity excess over PA-004 range (E-017) | Expenses | $3,500.00 |
|  | Subtotal — expenses |  | $73,221.34 |
|  | TOTAL RECOMMENDED DISALLOWANCE |  | $156,652.79 |
| Hold | E-001, E-002, E-003, E-016, E-017 balance | Expenses | $150,612.04 |

# 8. Recommended Actions

Return the invoice (§8.1, §7.3, §11.2(f)). Send written notice to Sandra Messina and Howard Blackwell III listing the adjustments and their basis (§8.2). The firm has 15 days from notice to dispute them.

Require a corrected LEDES 1998B submission with: reconciled subtotals and totals; Appendix A task codes; correct activity and expense codes; a TIMEKEEPER_NAME field; narratives of at least 30 words that match the Excel detail; and separate entries for block-billed tasks.

Request documentation: Voss and Huang invoices and cumulative billings to date; the CloudStar invoice (or confirmation that the Relativity platform is internal); the Meridian invoice for Torres and cumulative PA-003 spend; itemised courier charges; travel receipts and the flight itinerary; the Forrest Data Solutions engagement terms; the Brixton engagement terms; and Elaine Cho's July–September hours.

Require the §10.1 disclosures: a 75%-threshold notice with a revised 2024 budget, and a written explanation for the invoice exceeding $350,000. Schedule the lead-partner / General Counsel meeting if the projected overrun is more than 10%.

Decide on retroactive approvals (travel, Forrest, Brixton, Cho extension, Kwan) strictly under §9.3(b). If Cho's review work is still needed, require a new PA request before any further contract-attorney time is billed.

Pay undisputed amounts once the corrected invoice is received (§11.3), and never more than the stated total of $487,329.14 unless the firm formally re-invoices.

Put the firm on notice that repeated failures to obtain approval may lead to reconsideration of the engagement (§9.3(c), §11.2(g)). Remind it that no course of dealing waives the Guidelines (§12.3).

Housekeeping in VIH's own records: the Guidelines use both "Vanguard Industrial Holdings" and "Saxonbrook Industrial Holdings" for the client, and the Guidelines signature block is dated before the firm's acknowledgment. Exhibit A dates M. DeVries's approval to 12/12/2023 and lists A. Rosenberg on the original March 2023 team, while the approval log records 1/15/2024 and 5/10/2024 respectively. These discrepancies do not affect the October adjustments, but the records should be aligned before any dispute escalates.

# Appendix A — Fee Entries Under 30 Words (word counts)

Word counts are taken from the Excel "Professional Fees Detail" narratives. Entry 8 is the only one that meets the minimum.

Entry: word count

#1: 23; #2: 27; #3: 26; #4: 25; #5: 24; #6: 22; #7: 23; #8: 32; #9: 18; #10: 18

#11: 21; #12: 17; #13: 16; #14: 25; #15: 20; #16: 20; #17: 18; #18: 23; #19: 16; #20: 23

#21: 20; #22: 21; #23: 20; #24: 16; #25: 11; #26: 11; #27: 18; #28: 18; #29: 23; #30: 15

#31: 13; #32: 29; #33: 25; #34: 19; #35: 19; #36: 20; #37: 16; #38: 22; #39: 24; #40: 15

#41: 18; #42: 23; #43: 16; #44: 20; #45: 17; #46: 16; #47: 20; #48: 15; #49: 15; #50: 15

#51: 17; #52: 23; #53: 16; #54: 22; #55: 16; #56: 16; #57: 13; #58: 13; #59: 20; #60: 14

#61: 15; #62: 17; #63: 14; #64: 15; #65: 23; #66: 14; #67: 18; #68: 16; #69: 15; #70: 15

#71: 20; #72: 15; #73: 17; #74: 20; #75: 16; #76: 17; #77: 17; #78: 15; #79: 20; #80: 13

#81: 16; #82: 21; #83: 21; #84: 14; #85: 23; #86: 18; #87: 19; #88: 26; #89: 17; #90: 16

#91: 20; #92: 16; #93: 20; #94: 18; #95: 16; #96: 16; #97: 20; #98: 23; #99: 15; #100: 17

#101: 16; #102: 15; #103: 20; #104: 11; #105: 19; #106: 16; #107: 18; #108: 14; #109: 16; #110: 23

#111: 17; #112: 20; #113: 20; #114: 20; #115: 20; #116: 20; #117: 20; #118: 14; #119: 14; #120: 14

#121: 17; #122: 17; #123: 23; #124: 14; #125: 13; #126: 19; #127: 19; #128: 17; #129: 19; #130: 15

#131: 20; #132: 16; #133: 17; #134: 18; #135: 14; #136: 16; #137: 23; #138: 12; #139: 13